## Project Management Plan
Week | Backend | Frontend
2024-10-01 | build sytstem | build sytstem
2024-10-08 | test continues delivery | test continues delivery
2024-10-15 | API that return no data | connect to an API 1
2024-10-22 | Finish API 1 | finish map data to GUI for API 1
2024-10-29 | API 2 mock data | conect to an API 2
2024-11-05 | Finish API 2 | finish map data to GUI for AP 2
2024-11-12 | Intergation test | Intergation test
2024-11-19 | Bug fixing | Bug fixing
2024-11-26 | Ready for QA | Ready for QA
2024-12-03 | Deployed to QA | Deployed to QA
2024-12-10 | Test QA | Test QA
2024-12-17 | Deploy to PROD | Deploy to PROD
| Goals | Goals
| ML API | Deployed to Azure
| Logging | React